## Current Table
Indiana’s GLWQA DAP Action/Milestone Table (Updated 2/24/2020)
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
Draft DAP public noticed | 1. Develop draft DAP, as well as Milestone and Action Table |  | Advisory Committee | 8/2017 – 10/2017 |  | Complete
| 2. Develop PN with questions for comment period (60 days) |  | IDEM
| 3. Post draft DAP and Milestone and Action Table for PN and comment period. |  | IDEM, ISDA, and Advisory Committee
Determine priority areas | Use monitoring data | Water quality data, | Agencies completing monitoring and Advisory Committee subcommittee | 2017-11-01 |  | Complete
| map, WMP critical areas, | GIS, and NRCS spreadsheet
NRCS phosphorus export spreadsheet, and all ambient WQM data
Programs/Projects
Restore Natural Hydrology and Ecological Functions
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
Rethinking Drainage for the 21st Century workshop | 1. Workshop with county surveyors and drainage professionals to learn about activities and barriers | Staff time, travel, and meeting and implementation expenses | The Nature Conservancy and Purdue Extension | 2017-06-22 |  | First workshop held, additional workshops will follow
2. The goal is to establish an innovative drainage pilot project
Ecological maintenance of regulated & unregulated drains to reduce hydrological modification & maintenance needs | Convene a drainage work group with county surveyors, members of the drainage boards, stream ecology/watershed restoration professionals, and concerned citizens | Indiana demonstration sites, as well as scientific literature and current research findings | DAP Advisory Committee | 2018, on-going
Point Source, Urban
City of Fort Wayne LTCP (outlined at https://www.cityoffortwayne.org/utilities/162-clean-river-team/3208-long-term-control-plan.html) | Reduce CSOs to the St. Marys and Maumee Rivers | Staff time and implementation expenses |  | 2025
Stormwater NPDES MS4 Permit | Manage stormwater discharges | Staff time and implementation expenses
Municipal NPDES permit | Provide guidelines and standards for water quantity and quality management | Staff time and implementation expenses
Adams County RSD sewer extension | Extend sewer to unincorporated areas within Adams County, including the Town of Pleasant Mills | Staff time and implementation expenses
Nonpoint Source, Urban
Local ordinances and technical design standards | Provide guidelines and standards for water quantity and quality management | Staff time and implementation expenses | City of Fort Wayne Utilities |  |  | In progress
Revegetate urban stream banks with native plants in the Upper Maumee River | Work with local non-profits to organize native planting opportunities for the community | Two to three community events per year | Save Maumee |  |  | In progress
2016 through 2018 Installed over 3,600 linear feet of riparian buffers with woody vegetation in three Upper Maumee critical subwatersheds; Trier ditch (04100005010010), Bullerman (04100005010040), and Six-mile Creek (04100005010060) and 2019 through 2020 Installing 3,600 linear feet of riparian buffers with woody vegetation in 2 Upper Maumee critical subwatersheds; Trier ditch (04100005010010), Bullerman (04100005010040) | Organize 2 (not 3) native tree planting opportunities for the community annually | Work with local non-profits and local business | Save Maumee |  | Nitrogen 426.66 lb/yr, phosphorus 253.32 lb/yr, and sediment 253.34 tons/yr
Urban Clean Water Indiana Grant - Steuben County, reducing sediment and nutrients in waterbodies through implementation of urban conservation practices in dense residential areas located within 1/2-mile of a river, lake, shore, or perennial stream for improvement of water quality, wildlife habitat, and enhancing aesthetics | Implement cost-share program, reimbursing landowners 75% of all fees for design/implementation for rain gardens, tree and shrub plantings, water-edge enhancements (filter strips), and rain gardens. | 2018 Clean Water Indiana Urban Conservation Program grant; staff time, and landowner participation | Steuben County SWCD | 2020-12-31 |  | In progress
Nonpoint Source, Rural
Adams County emergency manure lagoons, one located north and one located south in Adams County | 1. One northern lagoon holding ten million gallons of manure | 1. Manure kept from excessive application and application on frozen ground | Adams County, local producers, and private landowners | 2018 |  | Complete
| 2. One southern lagoon holding 996,000 gallons of manure | 2. Sediment and nutrient load reductions
Phosphorus-Risk Reduction Pilot, 319(h) grant project, reimbursing for the reduction of phosphorus-risk potential by implementing conservation practices, including Black Creek (0410050104), Marsh Ditch | 1. Develop the phosphorus-risk reduction reimbursement program | 1. Phosphorus-risk calculator to determine the potential phosphorus-risk pre- and post- conservation practice implementation | Allen County SWCD, project partners, Advisory Committee, and Steering Committee | 2019-01-19 | 4,800 tons sediment, 8,300 lbs phosphorus, and 16,300 lbs nitrogen | In progress
(0410050106), Sixmile Creek (0410050103), Trier Ditch | 2. Implement the phosphorus-risk reduction reimbursement program | 2. Sediment and nutrient load reductions
(0410050102), and Bottern Ditch (0410050105)
Upper Maumee River Implementation, GLRI grant project, reducing nutrient and sediment loading through implementation of conservation practices, including Black Creek (0410050104), Marsh Ditch | 1. Develop a cost-share program targeting conservation practices addressing nutrient loss | Sediment and nutrient load reductions | Allen County SWCD, project partners, and Steering Committee | 2020-05-05 |  | In progress
(0410050106), Sixmile Creek (0410050103), and Trier Ditch | 2. Implement the cost-share program reimbursing the full cost of conservation practices
(0410050102). | 3. Conduct an education and outreach program to bring about behavioral change
St. Marys River Watershed Initiative, 319(h) grant project, implementing a paired watershed monitoring project, including the Weber Ditch (041000040502) and the Nickelsen Creek (041000040503) sub-watersheds | 1. Develop and implement a watershed-wide coordination program | 1. A water quality sample and conservation practice location database, a watershed conditions database, and a water quality database | Project Coordinator and project partners including Purdue University, Indiana Farm Bureau, Indiana Dairy Producers, Indiana Pork, Indiana State Poultry Association, Agri-Business Council of Indiana, Indiana Soybean Alliance, Indiana Corn Marketing Council, IDEM, as well as SWCD, NRCS, ISDA, and TNC staff located within the WLEB | 2021-06-05 |  | In progress
| 2. Develop and implement a targeted education and outreach program | 2. 4 Conservation practice demonstration workshops, 4 field days, and 4 tours
| 3. Develop and implement targeted social indicator surveyors | 3. 2 targeted social indicator survey events
| 4. Perform and complete paired watershed monitoring and modeling | 4. QAPP, monitoring program including equipment and protocols, and targeted watershed (L-THIA-LID) model
5. Perform and complete soil health monitoring
Reduce sediment and nutrient loading through installation and adoption of watershed land treatment practices | Administer grant and allocate funds for producers | 2015 IDNR LARE grant | DeKalb SWCD | 2018 |  | Completed Fall 2019
Reduce streambank erosion, repair streambank damage, and improve wildlife habitat through the City of Auburn | Complete feasibility study on Cedar Creek from Morning Star Road to Eckhart Park | IDNR LARE grant | DeKalb County | 2019-01-01 |  | Completed Spring 2019
Reduce sediment and nutrient runoff through adoption and installation of conservation practices | Cover crops, gypsum application, blind inlets, and streambank stabilization | 2017 CWI grant | DeKalb and Steuben County SWCDs | 2019-12-31 |  | Completed 12/31/2019
Submitted application for design work for two sites within the City of Auburn | Streambank stabilization / floodplain expansion | LARE | DeKalb County / City of Auburn | Submitted Jan. 2020 |  | In progress ; announcements made July 2020
Reduce nutrient loading from failed septic systems | Lead septic issues, update of ordinance, and provide cost-share funds for assisting with repair/replacement of septic systems | Updated Onsite Sewage System and Installation Ordinance and DeKalb County SWCD cost-share program | DeKalb County Health Department, Commissioners, and Supervisors, as well as Septic Issues Steering Committee | 2017-07-31 |  | Ordinance passed 7/31/2017
Support InField Advantage program by working with participants on data collection and nutrient stewardship (http://www.infieldadvantage.org/) | Help landowners/producers participating in the program to understand their nitrogen management plan | Group leaders time, ISDA staff time, and farmer/producer participation | ISDA and Group Leaders |  |  | In progress
Groups participating include:
1. INWL – WLEB group
2. INWA – Adams/Wells group
3. INST – Steuben/LaGrange group
Support rigorous enforcement of environmental rules & regulations | Determine legitimacy of claims of inconsistent implementation, identify barriers to execution, and establish a process for full implementation | Reports of violations and field surveys | IDEM, OISC, local SWCDs, and others TBD | 2018, on-going
4R Nutrient Stewardship Certification program | Identify willing landowners, apply for grants, install BMPs, and engage universities in on-farm research | Staff time and travel | The Nature Conservancy, Ohio Agribusiness Association, and Nutrient Stewardship Council | 80% of farmed acres under certified management by 2020 | Research in progress TBD, and goal is 40% reduction of TP and DRP by 2025 | Indiana has one certified facility and is in dialogue to start a 4R program
Steuben County SWCD District Cost-Share program to reduce sediment and nutrient loading through adoption and installation of conservation practices Establish woody plants for long-term erosion control and improvement of water quality, wildlife habitat, and enhanced aesthetics | Fourteen acres of trees planted within the West Branch, Fish Creek subwatershed Cover Crops and Tree/Shrub Establishment | District cost-share funding, staff time, and landowner/producer participation | Steuben County SWCD | on-going |  | On going, 26.7 acres of trees; 50 acres of cover crops established within West Branch of Fish Creek
Develop a response process for reports of manure mishandling & runoff from unregulated livestock operations or land application | Determine agency resources required | Current rules and regulations, as well as time and travel study model | IDEM, OISC, local SWCDs, and others TBD | 2018
Sustainable, functional septic systems throughout the WLEB via ordinances identifying best practices installation, maintenance & repair | Convene a WLEB septic system workgroup | Model ordinances and health department experts | WLEB local health departments with DAP support | 2018, on-going
Update Septic Issues-Collaborative Solutions Report | Outlines opportunities for connecting to sewer/ addressing failed septic systems. |  | DeKalb County Septic Issues steering committee |  |  | Completed 3/31/2019
Soil Health Partnership | Identify willing landowners, attend field days, and share results, as well as five to ten years of tillage, nutrient management, and cover crops | Staff time and travel | The Nature Conservancy, landowners, Soil Health Partnership, and local SWCDs | 2015, on-going | 1. Research in progress | In progress (five to ten years of tillage, nutrient management, and cover crops)
Cover crop discount program | Provide assistance to local small farmers for cover crops and education on benefits of cover crops | Demo Farm grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Monitoring
Secure GLRI grant for auto-sampler on the St. Marys River | Submit application |  | IDEM and USGS |  |  | Complete
Add capacity to sample for DRP laboratory analysis | Secure laboratory equipment for the ISDH | MOU between IDEM and ISDH, as well as IDEM lab account funding | IDEM and ISDH | 2017 |  | 100% Funds secured and MOU executed
Collect DRP at IDEM fixed stations in the WLEB | Investigate necessary resources for collecting and analyzing for DRP | Time and travel study | IDEM | 2017 |  | DRP sample collection and analysis began on 1/18
Collect TP, DRP, and nitrate-nitrite samples at 27 sites during recreational season | Tri-State Watershed Weekly Water Quality Monitoring program | TSWA, SJRWI, City of Fort Wayne, USDA ARS, and Allen SWCD support | TSWA and Allen SWCD |  |  | In progress
In-stream water quality | Monthly and storm grab samples at locations within Fish Creek watershed | Staff time, travel, lab work SJWI, Steuben County SWCD, and Joyce Foundation | Steuben County SWCD and the Nature Conservancy | 2014 through 2017 |  | Complete
Ecology of two-stage ditches | Macroinvertebrate sampling at constructed two-stage ditch sites in St. Joseph watershed | Staff time, travel, and lab work IPFW and Joyce Foundation | IPFW and the Nature Conservancy | 2015 through 2018 |  | In progress
Education and Outreach
In-stream water quality | Weekly sampling during recreation season and monthly sampling during non-recreation season at ten locations | Staff time, travel, and lab work | City of Fort Wayne Utilities | Annually |  | In progress
Use the WLEB GIS Story Map to showcase the conservation and monitoring activities going on in the Indiana WLEB watershed | Update Story Map annually, as necessary | ISDA staff and WLEB Story Map located at http://isda.maps.arcgis.com/apps/MapSeries/index.html?appid=75881b3341714bc28b5d820405accacb | ISDA |  |  | In progress
Continue to conduct the spring and fall cover crop and tillage transect survey in the counties in the WLEB (http://www.in.gov/isda/2383.htm) | Partnership staff in Adams, Allen, DeKalb, Noble, Steuben, and Wells counties will conduct this transect in the spring following planting on an annual or bi-annual basis | ICP staff and time | ICP | April through June, every two years, and October through December, annually |  | In progress
Report the nutrient load reductions for all ICP assisted conservation practices within the WLEB on an annual basis (http://www.in.gov/isda/3261.htm) | ISDA staff will use the Region 5 Model to analyze practices and show sediment and nutrient load reductions | Region 5 Model and | ISDA and ICP | March, annually | Sediment 34,000 tons/yr, | In progress
|  | ISDA staff time |  |  | Nitrogen 86,000 lbs/yr, and
phosphorus 42,000 lbs/yr
Provide soil health education to 100+ farmers, retailers, and CCAs | Seeing Green: Fields and Profits conservation day | NRCS GLRI grant, Soil Health Partnership (SHP), and Upper 319 grant | NRCS NE Area, SHP, Adams County and Allen County SWCD | 2017-08-10 |  | Complete
Educate producers on production practices related to water quality issues in the WLEB | Annual agronomy field day, held in conjunction with The Andersons, Purdue Extension, and surrounding SWCDs | Partial funding provided through 2015 and 2017 CWI grants | DeKalb and Steuben Counties | Annually |  | On going
Educate the public on the WLEB issues | Planned and implemented the Watershed-n-Spread event. Dr. Chad Penn presented “WLEB: the perfect storm” | Completed as part of the programing efforts of the SJRWI | SJRWI, Purdue Extension, City of Auburn, and DeKalb SWCD | 2017-03-02 |  | Complete
Educate producers/landowners on production/urban practices related to water quality issues in the WLEB | Annual meeting, presentations, various district workshops, booth at 4H Fair, and educational materials | Funding provided through District Base of Operations | Steuben County SWCD | Annually |  | In progress, hundreds impacted
Youth education | Educational materials provided on pollinators, soil health, trees, water quality, and summer conservation camps | Staff time, travel, and educational material fees | Steuben County SWCD and NE Conservation Districts | Annually |  | In progress, an average of 1,450 students, annually
Youth education for 32 years, hands-on educational event for 4th grade students of the Metropolitan School District of Steuben County to teach soil health water quality, and other conservation-related subjects | 4th grade youth conservation field day | Staff and volunteer time, travel, and educational material fees | Steuben County SWCD, Ralph E. Taylor Conservation Grant through the Steuben County Community Foundation | Annually |  | In progress, an average of 300 students, annually
Urban Clean Water Indiana Grant - Steuben County, reducing sediment and nutrients in waterbodies through education and outreach of urban conservation practices related to water quality issues | Conduct education and outreach programs to increase urban audiences’ awareness about water quality and soil conservation practices; help this segment of the population to rethink their properties and reduce their environmental impact. | 2018 Clean Water Indiana Urban Conservation Program grant, staff time, and landowner participation | Steuben County SWCD | 2020-12-31 |  | In progress
Educate homeowners/landowners urban practices related to water quality issues in the Maumee WLEB | Promote urban BMPs for storm water management from streets, parking lots, and other impervious pavement surfaces to community members and homeowners in the city | Funding through grants and in-kind donations (save maumee does not receive donations or funding to work on this issue. It is more of a byproduct of our work) | Save Maumee, City Utilities of Fort Wayne, and ACPWQ |  |  | In progress
Partner with local non-profits to harvest and collect native seeds | Seed harvest event in wetland, preserve, or natural habitat | Public and private land owners, as well as one to two local groups | Little River wetlands project, ACRES Land Trust, Save Maumee | Annually |  | In progress
Work with local non-profits to organize community urban stream bank restoration projects within the upper Maumee watershed | Collect/purchase 100 lbs 4 acres worth of native seeds planted on the stream and riverbanks and collect/ purchase 1,100 5,560 native trees to be planted on severely eroded riverbanks and streams; secure GLRI funding | One to two active local community non-profit groups | Save Maumee | Two seed harvest projects, annually and two tree planting projects in April and October, annually and 1 annual public trash removal in September | Nitrogen 426.66 lb/yr, phosphorus 253.32 lb/yr, and sediment 253.34 tons/yr | In progress
Sponsor and present at soil health, 4R, and farmer working group field days and events in IN | Two to three events/year, serve on Tri-State Watershed Alliance Board, and sponsor and help host annual expo | Staff time, travel, and sponsorship/exhibitor fees | The Nature Conservancy and event partners |  |  | In progress (direct contact with 1,000 WLEB stakeholders)
Youth education | River Camp | Hoosier Riverwatch, GoFishIN, and Project WET (education ages 8-12) | FWP&R, Environmental Resources Center, and ACPWQ | July 5-8, 2016 and August 7-11, 2017 |  | Complete
Youth and adult education | Johnny Appleseed Festival | Project WET, Project Wild, and HWHP (child and adult) | ACPWQ and Central Lions | September 19-20, 2015, September 17-18, 2016, and September 16-17, 2017 |  | Complete
Youth education | Izaak Walton League Conservation Camp | Project WET and Hoosier Riverwatch (ages 6-16) | IWL and ACPWQ | 6/25/2015 and 6/23/2016 |  | Complete
Youth education | Envirothon/aquatics | Hoosier Riverwatch (G10-12) | NE IN Schools, SWCDs, NRCS, IDNR, and ACPWQ | 3/19/2015 and 3/17/2016 |  | Complete
Youth education | Canterbury Day of Service | Project WET and Hoosier Riverwatch (G5-8) | Canterbury MS, TSWA, and ACPWQ | 5/20/2015, 5/26/2016, and |  | Complete
Provide education on cover crops, wetlands, filter strips, and wildlife habitat and water quality issues | Land management field day | CREP and Region 5 Model | Adams County SWCD, DNR, Little Turtle Wetland, NRCS, Davey Resources, NTFF, and ISDA | 2015 |  | Complete
Adult and youth education | Various pasture walks at farms, including the Amish | Cooperative Amish Outreach grant and Demo Farm grant | Adams County SWCD and NRCS | Annually |  | In progress
Public education on BMPs, soil health, watersheds, water quality, and pollinators | Booth at Adams County 4H Fair |  | Adams County SWCD | Annually |  | In progress, thousands impacted
Youth education | Earthworms, investigating soil health, frogs, owls, butterflies, and trees |  | Adams County SWCD | Annually |  | In progress, thousands impacted
For 22 years, all 6th graders from public, parochial, and homeschool attend to learn lessons in conservation | Splash event: watershed, common water, trees, pollinators, earthworms, nematodes, and soil health |  | Adams County SWCD | Annually |  | In progress, thousands impacted
Adult education | Various field days focused on water quality and soil health topics | Cooperative Amish Outreach grant, Demo Farm grant, and various other funding sources | Adams & Allen County SWCDs, and other partners | Annually |  | In progress, hundreds impacted
Provide education materials explaining the WLEB and how actions affect others (promotes BMPs), how watersheds are connected and effect one another, and proper management of manure and how it effects phosphorus in the soil | Adams County Watershed, Adams County Watershed Maps, and Manure Management Practices booklets | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2016 |  | Complete, hundreds dispersed
Education on cover crops and how it helps phosphorous levels on farms | Cover Crop PARP meeting | Center Seeds | Center Seeds, Purdue Extension, and Adams County SWCD | 2016 |  | Complete, over a hundred impacted
Public promotion of soil health and water quality (combined annual meeting of SWCD, Farm Bureau, and Pork Producers) | Ag extravaganza |  | Adams County SWCD, Pork Producers, and Farm Bureau | Annually |  | In progress, hundreds impacted
Education of proper management of manure and reducing our phosphorous and education on value of manure and the IN State Chemist standards | Winter ag meeting | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Designed and disbursed nutrient management packets to encourage manure management and to ease record keeping for our producers | Nutrient management packets | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Education on importance of soil testing and the levels of phosphorous, soil health and best management practices are encouraged, as well as follow-up meeting to interpret test and provide aerial map of farm | Soil testing | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 6/2015 through 6/2017 |  | Complete, over a hundred tests
Education on the importance of manure and its value and a follow-up farm visit | Manure tests | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 6/2015 through 6/2017 |  | Complete
Provide education on WLEB, phosphorous levels in our area, and water and marine life testing | OSU Stone Lab tour on Lake Erie | Demo Farm grant | Adams County SWCD, NRCS, and ISDA | 2017-06-01 |  | Complete
Two meetings (am and pm) regarding education on WLEB, effects on phosphorous, water quality, and benefits and use of gypsum | Connect the Dots water quality meeting | Amish Outreach grant, Dr. Chris Winslow | Adams County SWCD, NRCS, and ISDA | 2016-03-14 |  | Complete
Promote use and benefits of cover crops and no-till practices, specifically drill being modified to be pulled by horses or tractor | Purchase of new Land Pride 7’ no-till drill | Demo Farm grant | Adams County SWCD and NRCS | 2017-06-01 |  | Complete
Educate on a variety of stormwater and water quality related topics to neighborhood groups and other organizations | Speakers available to discuss stormwater and water quality related topics | Staff time, as well as meeting and material expenses | City of Fort Wayne Utilities |  |  | In progress
Hands-on rain garden workshops and incentives for City of Fort Wayne residents to install a rain garden | Hands-on rain garden workshop held locally in Fort Wayne to provide rain garden and stormwater education | Staff time, meeting and material expenses, travel expenses, and incentives to Fort Wayne residents | City of Fort Wayne Utilities | Annual meetings typically held in spring |  | In progress

## Sheet6
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
In-stream water quality | Weekly sampling during recreation season and monthly sampling during non-recreation season at ten locations | Staff time, travel, and lab work | City of Fort Wayne Utilities | Annually |  | In progress
Use the WLEB GIS Story Map to showcase the conservation and monitoring activities going on in the Indiana WLEB watershed | Update Story Map annually, as necessary | ISDA staff and WLEB Story Map located at http://isda.maps.arcgis.com/apps/MapSeries/index.html?appid=75881b3341714bc28b5d820405accacb | ISDA |  |  | In progress
Continue to conduct the spring and fall cover crop and tillage transect survey in the counties in the WLEB (http://www.in.gov/isda/2383.htm) | Partnership staff in Adams, Allen, DeKalb, Noble, Steuben, and Wells counties will conduct this transect in the spring following planting on an annual or bi-annual basis | ICP staff and time | ICP | April through June, every two years, and October through December, annually |  | In progress
Report the nutrient load reductions for all ICP assisted conservation practices within the WLEB on an annual basis (http://www.in.gov/isda/3261.htm) | ISDA staff will use the Region 5 Model to analyze practices and show sediment and nutrient load reductions | Region 5 Model and ISDA staff time | ISDA and ICP | March, annually | Sediment 34,000 tons/yr, Nitrogen 86,000 lbs/yr, and phosphorus 42,000 lbs/yr | In progress
Provide soil health education to 100+ farmers, retailers, and CCAs | Seeing Green: Fields and Profits conservation day | NRCS GLRI grant, Soil Health Partnership (SHP), and Upper 319 grant | NRCS NE Area, SHP, Adams County and Allen County SWCD | 42957 |  | Complete
Educate producers on production practices related to water quality issues in the WLEB | Annual agronomy field day, held in conjunction with The Andersons, Purdue Extension, and surrounding SWCDs | Partial funding provided through 2015 and 2017 CWI grants | DeKalb and Steuben Counties | Annually |  | On going
Educate the public on the WLEB issues | Planned and implemented the Watershed-n-Spread event. Dr. Chad Penn presented “WLEB: the perfect storm” | Completed as part of the programing efforts of the SJRWI | SJRWI, Purdue Extension, City of Auburn, and DeKalb SWCD | 42796 |  | Complete
Educate producers/landowners on production/urban practices related to water quality issues in the WLEB | Annual meeting, presentations, various district workshops, booth at 4H Fair, and educational materials | Funding provided through District Base of Operations | Steuben County SWCD | Annually |  | In progress, hundreds impacted
Youth education | Educational materials provided on pollinators, soil health, trees, water quality, and summer conservation camps | Staff time, travel, and educational material fees | Steuben County SWCD and NE Conservation Districts | Annually |  | In progress, an average of 1,450 students, annually
Youth education for 32 years, hands-on educational event for 4th grade students of the Metropolitan School District of Steuben County to teach soil health water quality, and other conservation-related subjects | 4th grade youth conservation field day | Staff and volunteer time, travel, and educational material fees | Steuben County SWCD, Ralph E. Taylor Conservation Grant through the Steuben County Community Foundation | Annually |  | In progress, an average of 300 students, annually
Urban Clean Water Indiana Grant - Steuben County, reducing sediment and nutrients in waterbodies through education and outreach of urban conservation practices related to water quality issues | Conduct education and outreach programs to increase urban audiences’ awareness about water quality and soil conservation practices; help this segment of the population to rethink their properties and reduce their environmental impact. | 2018 Clean Water Indiana Urban Conservation Program grant, staff time, and landowner participation | Steuben County SWCD | 44196 |  | In progress
Educate homeowners/landowners urban practices related to water quality issues in the Maumee WLEB | Promote urban BMPs for storm water management from streets, parking lots, and other impervious pavement surfaces to community members and homeowners in the city | Funding through grants and in-kind donations (save maumee does not receive donations or funding to work on this issue. It is more of a byproduct of our work) | Save Maumee, City Utilities of Fort Wayne, and ACPWQ |  |  | In progress
Partner with local non-profits to harvest and collect native seeds | Seed harvest event in wetland, preserve, or natural habitat | Public and private land owners, as well as one to two local groups | Little River wetlands project, ACRES Land Trust, Save Maumee | Annually |  | In progress
Work with local non-profits to organize community urban stream bank restoration projects within the upper Maumee watershed | Collect/purchase 100 lbs 4 acres worth of native seeds planted on the stream and riverbanks and collect/ purchase 1,100 5,560 native trees to be planted on severely eroded riverbanks and streams; secure GLRI funding | One to two active local community non-profit groups | Save Maumee | Two seed harvest projects, annually and two tree planting projects in April and October, annually and 1 annual public trash removal in September | Nitrogen 426.66 lb/yr, phosphorus 253.32 lb/yr, and sediment 253.34 tons/yr | In progress
Sponsor and present at soil health, 4R, and farmer working group field days and events in IN | Two to three events/year, serve on Tri-State Watershed Alliance Board, and sponsor and help host annual expo | Staff time, travel, and sponsorship/exhibitor fees | The Nature Conservancy and event partners |  |  | In progress (direct contact with 1,000 WLEB stakeholders)
Youth education | River Camp | Hoosier Riverwatch, GoFishIN, and Project WET (education ages 8-12) | FWP&R, Environmental Resources Center, and ACPWQ | July 5-8, 2016 and August 7-11, 2017 |  | Complete
Youth and adult education | Johnny Appleseed Festival | Project WET, Project Wild, and HWHP (child and adult) | ACPWQ and Central Lions | September 19-20, 2015, September 17-18, 2016, and September 16-17, 2017 |  | Complete
Youth education | Izaak Walton League Conservation Camp | Project WET and Hoosier Riverwatch (ages 6-16) | IWL and ACPWQ | 6/25/2015 and 6/23/2016 |  | Complete
Youth education | Envirothon/aquatics | Hoosier Riverwatch (G10-12) | NE IN Schools, SWCDs, NRCS, IDNR, and ACPWQ | 3/19/2015 and 3/17/2016 |  | Complete
Youth education | Canterbury Day of Service | Project WET and Hoosier Riverwatch (G5-8) | Canterbury MS, TSWA, and ACPWQ | 5/20/2015, 5/26/2016, and |  | Complete
Provide education on cover crops, wetlands, filter strips, and wildlife habitat and water quality issues | Land management field day | CREP and Region 5 Model | Adams County SWCD, DNR, Little Turtle Wetland, NRCS, Davey Resources, NTFF, and ISDA | 2015 |  | Complete
Adult and youth education | Various pasture walks at farms, including the Amish | Cooperative Amish Outreach grant and Demo Farm grant | Adams County SWCD and NRCS | Annually |  | In progress
Public education on BMPs, soil health, watersheds, water quality, and pollinators | Booth at Adams County 4H Fair |  | Adams County SWCD | Annually |  | In progress, thousands impacted
Youth education | Earthworms, investigating soil health, frogs, owls, butterflies, and trees |  | Adams County SWCD | Annually |  | In progress, thousands impacted
For 22 years, all 6th graders from public, parochial, and homeschool attend to learn lessons in conservation | Splash event: watershed, common water, trees, pollinators, earthworms, nematodes, and soil health |  | Adams County SWCD | Annually |  | In progress, thousands impacted
Adult education | Various field days focused on water quality and soil health topics | Cooperative Amish Outreach grant, Demo Farm grant, and various other funding sources | Adams & Allen County SWCDs, and other partners | Annually |  | In progress, hundreds impacted
Provide education materials explaining the WLEB and how actions affect others (promotes BMPs), how watersheds are connected and effect one another, and proper management of manure and how it effects phosphorus in the soil | Adams County Watershed, Adams County Watershed Maps, and Manure Management Practices booklets | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2016 |  | Complete, hundreds dispersed
Education on cover crops and how it helps phosphorous levels on farms | Cover Crop PARP meeting | Center Seeds | Center Seeds, Purdue Extension, and Adams County SWCD | 2016 |  | Complete, over a hundred impacted
Public promotion of soil health and water quality (combined annual meeting of SWCD, Farm Bureau, and Pork Producers) | Ag extravaganza |  | Adams County SWCD, Pork Producers, and Farm Bureau | Annually |  | In progress, hundreds impacted
Education of proper management of manure and reducing our phosphorous and education on value of manure and the IN State Chemist standards | Winter ag meeting | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Designed and disbursed nutrient management packets to encourage manure management and to ease record keeping for our producers | Nutrient management packets | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Education on importance of soil testing and the levels of phosphorous, soil health and best management practices are encouraged, as well as follow-up meeting to interpret test and provide aerial map of farm | Soil testing | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 6/2015 through 6/2017 |  | Complete, over a hundred tests
Education on the importance of manure and its value and a follow-up farm visit | Manure tests | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 6/2015 through 6/2017 |  | Complete
Provide education on WLEB, phosphorous levels in our area, and water and marine life testing | OSU Stone Lab tour on Lake Erie | Demo Farm grant | Adams County SWCD, NRCS, and ISDA | 42887 |  | Complete
Two meetings (am and pm) regarding education on WLEB, effects on phosphorous, water quality, and benefits and use of gypsum | Connect the Dots water quality meeting | Amish Outreach grant, Dr. Chris Winslow | Adams County SWCD, NRCS, and ISDA | 42443 |  | Complete
Promote use and benefits of cover crops and no-till practices, specifically drill being modified to be pulled by horses or tractor | Purchase of new Land Pride 7’ no-till drill | Demo Farm grant | Adams County SWCD and NRCS | 42887 |  | Complete
Educate on a variety of stormwater and water quality related topics to neighborhood groups and other organizations | Speakers available to discuss stormwater and water quality related topics | Staff time, as well as meeting and material expenses | City of Fort Wayne Utilities |  |  | In progress
Hands-on rain garden workshops and incentives for City of Fort Wayne residents to install a rain garden | Hands-on rain garden workshop held locally in Fort Wayne to provide rain garden and stormwater education | Staff time, meeting and material expenses, travel expenses, and incentives to Fort Wayne residents | City of Fort Wayne Utilities | Annual meetings typically held in spring |  | In progress

## Sheet5
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
Secure GLRI grant for auto-sampler on the St. Marys River | Submit application |  | IDEM and USGS |  |  | Complete
Add capacity to sample for DRP laboratory analysis | Secure laboratory equipment for the ISDH | MOU between IDEM and ISDH, as well as IDEM lab account funding | IDEM and ISDH | 2017 |  | 100% Funds secured and MOU executed
Collect DRP at IDEM fixed stations in the WLEB | Investigate necessary resources for collecting and analyzing for DRP | Time and travel study | IDEM | 2017 |  | DRP sample collection and analysis began on 1/18
Collect TP, DRP, and nitrate-nitrite samples at 27 sites during recreational season | Tri-State Watershed Weekly Water Quality Monitoring program | TSWA, SJRWI, City of Fort Wayne, USDA ARS, and Allen SWCD support | TSWA and Allen SWCD |  |  | In progress
In-stream water quality | Monthly and storm grab samples at locations within Fish Creek watershed | Staff time, travel, lab work SJWI, Steuben County SWCD, and Joyce Foundation | Steuben County SWCD and the Nature Conservancy | 2014 through 2017 |  | Complete
Ecology of two-stage ditches | Macroinvertebrate sampling at constructed two-stage ditch sites in St. Joseph watershed | Staff time, travel, and lab work IPFW and Joyce Foundation | IPFW and the Nature Conservancy | 2015 through 2018 |  | In progress

## Sheet4
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
Adams County emergency manure lagoons, one located north and one located south in Adams County | 1. One northern lagoon holding ten million gallons of manure 2. One southern lagoon holding 996,000 gallons of manure | 1. Manure kept from excessive application and application on frozen ground 2. Sediment and nutrient load reductions | Adams County, local producers, and private landowners | 2018 |  | Complete
Phosphorus-Risk Reduction Pilot, 319(h) grant project, reimbursing for the reduction of phosphorus-risk potential by implementing conservation practices, including Black Creek (0410050104), Marsh Ditch (0410050106), Sixmile Creek (0410050103), Trier Ditch (0410050102), and Bottern Ditch (0410050105) | 1. Develop the phosphorus-risk reduction reimbursement program 2. Implement the phosphorus-risk reduction reimbursement program | 1. Phosphorus-risk calculator to determine the potential phosphorus-risk pre- and post- conservation practice implementation 2. Sediment and nutrient load reductions | Allen County SWCD, project partners, Advisory Committee, and Steering Committee | 43484 | 4,800 tons sediment, 8,300 lbs phosphorus, and 16,300 lbs nitrogen | In progress
Upper Maumee River Implementation, GLRI grant project, reducing nutrient and sediment loading through implementation of conservation practices, including Black Creek (0410050104), Marsh Ditch (0410050106), Sixmile Creek (0410050103), and Trier Ditch (0410050102). | 1. Develop a cost-share program targeting conservation practices addressing nutrient loss 2. Implement the cost-share program reimbursing the full cost of conservation practices 3. Conduct an education and outreach program to bring about behavioral change | Sediment and nutrient load reductions | Allen County SWCD, project partners, and Steering Committee | 43956 |  | In progress
St. Marys River Watershed Initiative, 319(h) grant project, implementing a paired watershed monitoring project, including the Weber Ditch (041000040502) and the Nickelsen Creek (041000040503) sub-watersheds | 1. Develop and implement a watershed-wide coordination program 2. Develop and implement a targeted education and outreach program 3. Develop and implement targeted social indicator surveyors 4. Perform and complete paired watershed monitoring and modeling 5. Perform and complete soil health monitoring | 1. A water quality sample and conservation practice location database, a watershed conditions database, and a water quality database 2. 4 Conservation practice demonstration workshops, 4 field days, and 4 tours 3. 2 targeted social indicator survey events 4. QAPP, monitoring program including equipment and protocols, and targeted watershed (L-THIA-LID) model | Project Coordinator and project partners including Purdue University, Indiana Farm Bureau, Indiana Dairy Producers, Indiana Pork, Indiana State Poultry Association, Agri-Business Council of Indiana, Indiana Soybean Alliance, Indiana Corn Marketing Council, IDEM, as well as SWCD, NRCS, ISDA, and TNC staff located within the WLEB | 44352 |  | In progress
Reduce sediment and nutrient loading through installation and adoption of watershed land treatment practices | Administer grant and allocate funds for producers | 2015 IDNR LARE grant | DeKalb SWCD | 2018 |  | Completed Fall 2019
Reduce streambank erosion, repair streambank damage, and improve wildlife habitat through the City of Auburn | Complete feasibility study on Cedar Creek from Morning Star Road to Eckhart Park | IDNR LARE grant | DeKalb County | 43466 |  | Completed Spring 2019
Reduce sediment and nutrient runoff through adoption and installation of conservation practices | Cover crops, gypsum application, blind inlets, and streambank stabilization | 2017 CWI grant | DeKalb and Steuben County SWCDs | 43830 |  | Completed 12/31/2019
Submitted application for design work for two sites within the City of Auburn | Streambank stabilization / floodplain expansion | LARE | DeKalb County / City of Auburn | Submitted Jan. 2020 |  | In progress ; announcements made July 2020
Reduce nutrient loading from failed septic systems | Lead septic issues, update of ordinance, and provide cost-share funds for assisting with repair/replacement of septic systems | Updated Onsite Sewage System and Installation Ordinance and DeKalb County SWCD cost-share program | DeKalb County Health Department, Commissioners, and Supervisors, as well as Septic Issues Steering Committee | 42947 |  | Ordinance passed 7/31/2017
Support InField Advantage program by working with participants on data collection and nutrient stewardship (http://www.infieldadvantage.org/) | Help landowners/producers participating in the program to understand their nitrogen management plan Groups participating include: 1. INWL – WLEB group 2. INWA – Adams/Wells group 3. INST – Steuben/LaGrange group | Group leaders time, ISDA staff time, and farmer/producer participation | ISDA and Group Leaders |  |  | In progress
Support rigorous enforcement of environmental rules & regulations | Determine legitimacy of claims of inconsistent implementation, identify barriers to execution, and establish a process for full implementation | Reports of violations and field surveys | IDEM, OISC, local SWCDs, and others TBD | 2018, on-going
4R Nutrient Stewardship Certification program | Identify willing landowners, apply for grants, install BMPs, and engage universities in on-farm research | Staff time and travel | The Nature Conservancy, Ohio Agribusiness Association, and Nutrient Stewardship Council | 80% of farmed acres under certified management by 2020 | Research in progress TBD, and goal is 40% reduction of TP and DRP by 2025 | Indiana has one certified facility and is in dialogue to start a 4R program
Steuben County SWCD District Cost-Share program to reduce sediment and nutrient loading through adoption and installation of conservation practices Establish woody plants for long-term erosion control and improvement of water quality, wildlife habitat, and enhanced aesthetics | Fourteen acres of trees planted within the West Branch, Fish Creek subwatershed Cover Crops and Tree/Shrub Establishment | District cost-share funding, staff time, and landowner/producer participation | Steuben County SWCD | on-going |  | On going, 26.7 acres of trees; 50 acres of cover crops established within West Branch of Fish Creek
Develop a response process for reports of manure mishandling & runoff from unregulated livestock operations or land application | Determine agency resources required | Current rules and regulations, as well as time and travel study model | IDEM, OISC, local SWCDs, and others TBD | 2018
Sustainable, functional septic systems throughout the WLEB via ordinances identifying best practices installation, maintenance & repair | Convene a WLEB septic system workgroup | Model ordinances and health department experts | WLEB local health departments with DAP support | 2018, on-going
Update Septic Issues-Collaborative Solutions Report | Outlines opportunities for connecting to sewer/ addressing failed septic systems. |  | DeKalb County Septic Issues steering committee |  |  | Completed 3/31/2019
Soil Health Partnership | Identify willing landowners, attend field days, and share results, as well as five to ten years of tillage, nutrient management, and cover crops | Staff time and travel | The Nature Conservancy, landowners, Soil Health Partnership, and local SWCDs | 2015, on-going | 1. Research in progress | In progress (five to ten years of tillage, nutrient management, and cover crops)
Cover crop discount program | Provide assistance to local small farmers for cover crops and education on benefits of cover crops | Demo Farm grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete

## Sheet3
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
Local ordinances and technical design standards | Provide guidelines and standards for water quantity and quality management | Staff time and implementation expenses | City of Fort Wayne Utilities |  |  | In progress
Revegetate urban stream banks with native plants in the Upper Maumee River | Work with local non-profits to organize native planting opportunities for the community | Two to three community events per year | Save Maumee |  |  | In progress
2016 through 2018 Installed over 3,600 linear feet of riparian buffers with woody vegetation in three Upper Maumee critical subwatersheds; Trier ditch (04100005010010), Bullerman (04100005010040), and Six-mile Creek (04100005010060) and 2019 through 2020 Installing 3,600 linear feet of riparian buffers with woody vegetation in 2 Upper Maumee critical subwatersheds; Trier ditch (04100005010010), Bullerman (04100005010040) | Organize 2 (not 3) native tree planting opportunities for the community annually | Work with local non-profits and local business | Save Maumee |  | Nitrogen 426.66 lb/yr, phosphorus 253.32 lb/yr, and sediment 253.34 tons/yr
Urban Clean Water Indiana Grant - Steuben County, reducing sediment and nutrients in waterbodies through implementation of urban conservation practices in dense residential areas located within 1/2-mile of a river, lake, shore, or perennial stream for improvement of water quality, wildlife habitat, and enhancing aesthetics | Implement cost-share program, reimbursing landowners 75% of all fees for design/implementation for rain gardens, tree and shrub plantings, water-edge enhancements (filter strips), and rain gardens. | 2018 Clean Water Indiana Urban Conservation Program grant; staff time, and landowner participation | Steuben County SWCD | 44196 |  | In progress

## Sheet2
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
City of Fort Wayne LTCP (outlined at https://www.cityoffortwayne.org/utilities/162-clean-river-team/3208-long-term-control-plan.html) | Reduce CSOs to the St. Marys and Maumee Rivers | Staff time and implementation expenses |  | 2025
Stormwater NPDES MS4 Permit | Manage stormwater discharges | Staff time and implementation expenses
Municipal NPDES permit | Provide guidelines and standards for water quantity and quality management | Staff time and implementation expenses
Adams County RSD sewer extension | Extend sewer to unincorporated areas within Adams County, including the Town of Pleasant Mills | Staff time and implementation expenses

## Sheet1
Restore Natural Hydrology and Ecological Functions
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
Rethinking Drainage for the 21st Century workshop | 1. Workshop with county surveyors and drainage professionals to learn about activities and barriers 2. The goal is to establish an innovative drainage pilot project | Staff time, travel, and meeting and implementation expenses | The Nature Conservancy and Purdue Extension | 42908 |  | First workshop held, additional workshops will follow
Ecological maintenance of regulated & unregulated drains to reduce hydrological modification & maintenance needs | Convene a drainage work group with county surveyors, members of the drainage boards, stream ecology/watershed restoration professionals, and concerned citizens | Indiana demonstration sites, as well as scientific literature and current research findings | DAP Advisory Committee | 2018, on-going

## Updates
Updates Received from: | Date
Save Maumee | 2019-01-07
DeKalb County (Allen Haynes) | 2020-01-29
Stueben County (Janel Meyer) | 2020-02-14

## Old Table
Indiana’s GLWQA DAP Action/Milestone Table (Updated 1/25/2018)
Objectives/Goals | Action/Activity | Tools/Resources | Responsible Parties | Time-frame | Target Reduction | Outcomes
Draft DAP public noticed | 1. Develop draft DAP, as well as Milestone and Action Table |  | Advisory Committee | 8/2017 – 10/2017 |  | Complete
| 2. Develop PN with questions for comment period (60 days) |  | IDEM
| 3. Post draft DAP and Milestone and Action Table for PN and comment period. |  | IDEM, ISDA, and Advisory Committee
Determine priority areas | Use monitoring data | Water quality data, | Agencies completing monitoring and Advisory Committee subcommittee | 2017-11-01 |  | Complete
| map, WMP critical areas, | GIS, and NRCS spreadsheet
NRCS phosphorus export spreadsheet, and all ambient WQM data
Programs/Projects
Restore Natural Hydrology and Ecological Functions
Rethinking Drainage for the 21st Century workshop | 1. Workshop with county surveyors and drainage professionals to learn about activities and barriers | Staff time, travel, and meeting and implementation expenses | The Nature Conservancy and Purdue Extension | 2017-06-22 |  | First workshop held, additional workshops will follow
2. The goal is to establish an innovative drainage pilot project
Ecological maintenance of regulated & unregulated drains to reduce hydrological modification & maintenance needs | Convene a drainage work group with county surveyors, members of the drainage boards, stream ecology/watershed restoration professionals, and concerned citizens | Indiana demonstration sites, as well as scientific literature and current research findings | DAP Advisory Committee | 2018, on-going
Point Source, Urban
City of Fort Wayne LTCP (outlined at https://www.cityoffortwayne.org/utilities/162-clean-river-team/3208-long-term-control-plan.html) | Reduce CSOs to the St. Marys and Maumee Rivers | Staff time and implementation expenses |  | 2025
Stormwater NPDES MS4 Permit | Manage stormwater discharges | Staff time and implementation expenses
Municipal NPDES permit | Provide guidelines and standards for water quantity and quality management | Staff time and implementation expenses
Adams County RSD sewer extension | Extend sewer to unincorporated areas within Adams County, including the Town of Pleasant Mills | Staff time and implementation expenses
Nonpoint Source, Urban
Local ordinances and technical design standards | Provide guidelines and standards for water quantity and quality management | Staff time and implementation expenses | City of Fort Wayne Utilities |  |  | In progress
Revegetate urban stream banks with native plants in the Upper Maumee River | Work with local non-profits to organize native planting opportunities for the community | Two to three community events per year | Save Maumee |  |  | In progress
Install 7,200 linear feet of riparian buffers with woody vegetation in three Upper Maumee critical subwatersheds; Trier ditch (04100005010010), Bullerman (04100005010040), and Six-mile Creek (04100005010060) | Organize three native tree planting opportunities for the community | Work with local non-profits | Save Maumee |  | Nitrogen 426.66 lb/yr, phosphorus 253.32 lb/yr, and sediment 253.34 tons/yr
Nonpoint Source, Rural
Adams County emergency manure lagoons, one located north and one located south in Adams County | 1. One northern lagoon holding ten million gallons of manure | 1. Manure kept from excessive application and application on frozen ground | Adams County, local producers, and private landowners | 2018 |  | In progress
| 2. One southern lagoon holding 996,000 gallons of manure | 2. Sediment and nutrient load reductions
Phosphorus-Risk Reduction Pilot, 319(h) grant project, reimbursing for the reduction of phosphorus-risk potential by implementing conservation practices, including Black Creek (0410050104), Marsh Ditch | 1. Develop the phosphorus-risk reduction reimbursement program | 1. Phosphorus-risk calculator to determine the potential phosphorus-risk pre- and post- conservation practice implementation | Allen County SWCD, project partners, Advisory Committee, and Steering Committee | 2019-01-19 | 4,800 tons sediment, 8,300 lbs phosphorus, and 16,300 lbs nitrogen | In progress
(0410050106), Sixmile Creek (0410050103), Trier Ditch | 2. Implement the phosphorus-risk reduction reimbursement program | 2. Sediment and nutrient load reductions
(0410050102), and Bottern Ditch (0410050105)
Upper Maumee River Implementation, GLRI grant project, reducing nutrient and sediment loading through implementation of conservation practices, including Black Creek (0410050104), Marsh Ditch | 1. Develop a cost-share program targeting conservation practices addressing nutrient loss | Sediment and nutrient load reductions | Allen County SWCD, project partners, and Steering Committee | 2020-05-05 |  | In progress
(0410050106), Sixmile Creek (0410050103), and Trier Ditch | 2. Implement the cost-share program reimbursing the full cost of conservation practices
(0410050102). | 3. Conduct an education and outreach program to bring about behavioral change
St. Marys River Watershed Initiative, 319(h) grant project, implementing a paired watershed monitoring project, including the Weber Ditch (041000040502) and the Nickelsen Creek (041000040503) sub-watersheds | 1. Develop and implement a watershed-wide coordination program | 1. A water quality sample and conservation practice location database, a watershed conditions database, and a water quality database | Project Coordinator and project partners including Purdue University, Indiana Farm Bureau, Indiana Dairy Producers, Indiana Pork, Indiana State Poultry Association, Agri-Business Council of Indiana, Indiana Soybean Alliance, Indiana Corn Marketing Council, IDEM, as well as SWCD, NRCS, ISDA, and TNC staff located within the WLEB | 2021-06-05 |  | In progress
| 2. Develop and implement a targeted education and outreach program | 2. 4 Conservation practice demonstration workshops, 4 field days, and 4 tours
| 3. Develop and implement targeted social indicator surveyors | 3. 2 targeted social indicator survey events
| 4. Perform and complete paired watershed monitoring and modeling | 4. QAPP, monitoring program including equipment and protocols, and targeted watershed (L-THIA-LID) model
5. Perform and complete soil health monitoring
Reduce sediment and nutrient loading through installation and adoption of watershed land treatment practices | Administer grant and allocate funds for producers | 2015 IDNR LARE grant | DeKalb SWCD | 2018 |  | In progress
Reduce streambank erosion, repair streambank damage, and improve wildlife habitat through the City of Auburn | Complete feasibility study on Cedar Creek from Morning Star Road to Eckhart Park | IDNR LARE grant | DeKalb County | 2019-01-01 |  | In progress
Reduce sediment and nutrient runoff through adoption and installation of conservation practices | Cover crops, gypsum application, blind inlets, and streambank stabilization | 2017 CWI grant | DeKalb and Steuben County SWCDs | 2019-12-31 |  | In progress
Reduce nutrient loading from failed septic systems | Lead septic issues, update of ordinance, and provide cost-share funds for assisting with repair/replacement of septic systems | Updated Onsite Sewage System and Installation Ordinance and DeKalb County SWCD cost-share program | DeKalb County Health Department, Commissioners, and Supervisors, as well as Septic Issues Steering Committee | 2017-07-31 |  | Ordinance passed 7/31/2017
Support InField Advantage program by working with participants on data collection and nutrient stewardship (http://www.infieldadvantage.org/) | Help landowners/producers participating in the program to understand their nitrogen management plan | Group leaders time, ISDA staff time, and farmer/producer participation | ISDA and Group Leaders |  |  | In progress
Groups participating include:
1. INWL – WLEB group
2. INWA – Adams/Wells group
3. INST – Steuben/LaGrange group
Support rigorous enforcement of environmental rules & regulations | Determine legitimacy of claims of inconsistent implementation, identify barriers to execution, and establish a process for full implementation | Reports of violations and field surveys | IDEM, OISC, local SWCDs, and others TBD | 2018, on-going
4R Nutrient Stewardship Certification program | Identify willing landowners, apply for grants, install BMPs, and engage universities in on-farm research | Staff time and travel | The Nature Conservancy, Ohio Agribusiness Association, and Nutrient Stewardship Council | 80% of farmed acres under certified management by 2020 | Research in progress TBD, and goal is 40% reduction of TP and DRP by 2025 | Indiana has one certified facility and is in dialogue to start a 4R program
Establish woody plants for long-term erosion control and improvement of water quality, enhancing aesthetics, and wildlife habitat | Fourteen acres of trees planted within the West Branch, Fish Creek subwatershed | District cost-share funding | Steuben County SWCD |  |  | Completed 2016 and 2017
Develop a response process for reports of manure mishandling & runoff from unregulated livestock operations or land application | Determine agency resources required | Current rules and regulations, as well as time and travel study model | IDEM, OISC, local SWCDs, and others TBD | 2018
Sustainable, functional septic systems throughout the WLEB via ordinances identifying best practices installation, maintenance & repair | Convene a WLEB septic system workgroup | Model ordinances and health department experts | WLEB local health departments with DAP support | 2018, on-going
Soil Health Partnership | Identify willing landowners, attend field days, and share results, as well as five to ten years of tillage, nutrient management, and cover crops | Staff time and travel | The Nature Conservancy, landowners, Soil Health Partnership, and local SWCDs | 2015, on-going | 1. Research in progress | In progress (five to ten years of tillage, nutrient management, and cover crops)
Cover crop discount program | Provide assistance to local small farmers for cover crops and education on benefits of cover crops | Demo Farm grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Monitoring
Secure GLRI grant for auto-sampler on the St. Marys River | Submit application |  | IDEM and USGS |  |  | Complete
Add capacity to sample for DRP laboratory analysis | Secure laboratory equipment for the ISDH | MOU between IDEM and ISDH, as well as IDEM lab account funding | IDEM and ISDH | 2017 |  | 100% Funds secured and MOU executed
Collect DRP at IDEM fixed stations in the WLEB | Investigate necessary resources for collecting and analyzing for DRP | Time and travel study | IDEM | 2017 |  | DRP sample collection and analysis began on 1/18
Collect TP, DRP, and nitrate-nitrite samples at 27 sites during recreational season | Tri-State Watershed Weekly Water Quality Monitoring program | TSWA, SJRWI, City of Fort Wayne, USDA ARS, and Allen SWCD support | TSWA and Allen SWCD |  |  | In progress
In-stream water quality | Monthly and storm grab samples at locations within Fish Creek watershed | Staff time, travel, lab work SJWI, Steuben County SWCD, and Joyce Foundation | Steuben County SWCD and the Nature Conservancy | 2014 through 2017 |  | Complete
Ecology of two-stage ditches | Macroinvertebrate sampling at constructed two-stage ditch sites in St. Joseph watershed | Staff time, travel, and lab work IPFW and Joyce Foundation | IPFW and the Nature Conservancy | 2015 through 2018 |  | In progress
Education and Outreach
In-stream water quality | Weekly sampling during recreation season and monthly sampling during non-recreation season at ten locations | Staff time, travel, and lab work | City of Fort Wayne Utilities | Annually |  | In progress
Use the WLEB GIS Story Map to showcase the conservation and monitoring activities going on in the Indiana WLEB watershed | Update Story Map annually, as necessary | ISDA staff and WLEB Story Map located at http://isda.maps.arcgis.com/apps/MapSeries/index.html?appid=75881b3341714bc28b5d820405accacb | ISDA |  |  | In progress
Continue to conduct the spring and fall cover crop and tillage transect survey in the counties in the WLEB (http://www.in.gov/isda/2383.htm) | Partnership staff in Adams, Allen, DeKalb, Noble, Steuben, and Wells counties will conduct this transect in the spring following planting on an annual or bi-annual basis | ICP staff and time | ICP | April through June, every two years, and October through December, annually |  | In progress
Report the nutrient load reductions for all ICP assisted conservation practices within the WLEB on an annual basis (http://www.in.gov/isda/3261.htm) | ISDA staff will use the Region 5 Model to analyze practices and show sediment and nutrient load reductions | Region 5 Model and | ISDA and ICP | March, annually | Sediment 34,000 tons/yr, | In progress
|  | ISDA staff time |  |  | Nitrogen 86,000 lbs/yr, and
phosphorus 42,000 lbs/yr
Provide soil health education to 100+ farmers, retailers, and CCAs | Seeing Green: Fields and Profits conservation day | NRCS GLRI grant, Soil Health Partnership (SHP), and Upper 319 grant | NRCS NE Area, SHP, Adams County and Allen County SWCD | 2017-08-10 |  | Complete
Educate producers on production practices related to water quality issues in the WLEB | Annual agronomy field day, held in conjunction with The Andersons, Purdue Extension, and surrounding SWCDs | Partial funding provided through 2015 and 2017 CWI grants | DeKalb and Steuben Counties | Annually |  | On going
Educate the public on the WLEB issues | Planned and implemented the Watershed-n-Spread event. Dr. Chad Penn presented “WLEB: the perfect storm” | Completed as part of the programing efforts of the SJRWI | SJRWI, Purdue Extension, City of Auburn, and DeKalb SWCD | 2017-03-02 |  | Complete
Educate producers/landowners on production/urban practices related to water quality issues in the WLEB | Annual meeting, presentations, various district workshops, booth at 4H Fair, and educational materials | Funding provided through District Base of Operations | Steuben County SWCD | Annually |  | In progress, hundreds impacted
Youth education | Educational materials provided on pollinators, soil health, trees, water quality, and summer conservation camps | Staff time, travel, and educational material fees | Steuben County SWCD and NE Conservation Districts | Annually |  | In progress, an average of 1,450 students, annually
Youth education for 32 years, hands-on educational event for 4th grade students of the Metropolitan School District of Steuben County to teach soil health water quality, and other conservation-related subjects | 4th grade youth conservation field day | Staff and volunteer time, travel, and educational material fees | Steuben County SWCD | Annually |  | In progress, an average of 300 students, annually
Educate homeowners/landowners urban practices related to water quality issues in the Maumee WLEB | Promote urban BMPs for storm water management from streets, parking lots, and other impervious pavement surfaces to community members and homeowners in the city | Funding through grants and in-kind donations (save maumee does not receive donations or funding to work on this issue. It is more of a byproduct of our work) | Save Maumee, City Utilities of Fort Wayne, and ACPWQ |  |  | In progress
Partner with local non-profits to harvest and collect native seeds | Seed harvest event in wetland, preserve, or natural habitat | Public and private land owners, as well as one to two local groups | Little River wetlands project, ACRES Land Trust, Save Maumee | Annually |  | In progress
Work with local non-profits to organize community urban stream bank restoration projects within the upper Maumee watershed | Collect/purchase 100lbs (4 acres of coverage) native seeds to be planted on the stream and riverbanks and collect/ purchase 1,100 5,560 native trees planted on severely eroded riverbanks and streams; secure GLRI funding | One to two active local community non-profit groups | Save Maumee | Two seed harvest projects, annually and two tree planting projects in April and October, annually and 1 annual public trash removal in September | Nitrogen 426.66 lb/yr, phosphorus 253.32 lb/yr, and sediment 253.34 tons/yr | In progress
Sponsor and present at soil health, 4R, and farmer working group field days and events in IN | Two to three events/year, serve on Tri-State Watershed Alliance Board, and sponsor and help host annual expo | Staff time, travel, and sponsorship/exhibitor fees | The Nature Conservancy and event partners |  |  | In progress (direct contact with 1,000 WLEB stakeholders)
Youth education | River Camp | Hoosier Riverwatch, GoFishIN, and Project WET (education ages 8-12) | FWP&R, Environmental Resources Center, and ACPWQ | July 5-8, 2016 and August 7-11, 2017 |  | Complete
Youth and adult education | Johnny Appleseed Festival | Project WET, Project Wild, and HWHP (child and adult) | ACPWQ and Central Lions | September 19-20, 2015, September 17-18, 2016, and September 16-17, 2017 |  | Complete
Youth education | Izaak Walton League Conservation Camp | Project WET and Hoosier Riverwatch (ages 6-16) | IWL and ACPWQ | 6/25/2015 and 6/23/2016 |  | Complete
Youth education | Envirothon/aquatics | Hoosier Riverwatch (G10-12) | NE IN Schools, SWCDs, NRCS, IDNR, and ACPWQ | 3/19/2015 and 3/17/2016 |  | Complete
Youth education | Canterbury Day of Service | Project WET and Hoosier Riverwatch (G5-8) | Canterbury MS, TSWA, and ACPWQ | 5/20/2015, 5/26/2016, and |  | Complete
Provide education on cover crops, wetlands, filter strips, and wildlife habitat and water quality issues | Land management field day | CREP and Region 5 Model | Adams County SWCD, DNR, Little Turtle Wetland, NRCS, Davey Resources, NTFF, and ISDA | 2015 |  | Complete
Adult and youth education | Various pasture walks at farms, including the Amish | Cooperative Amish Outreach grant and Demo Farm grant | Adams County SWCD and NRCS | Annually |  | In progress
Public education on BMPs, soil health, watersheds, water quality, and pollinators | Booth at Adams County 4H Fair |  | Adams County SWCD | Annually |  | In progress, thousands impacted
Youth education | Earthworms, investigating soil health, frogs, owls, butterflies, and trees |  | Adams County SWCD | Annually |  | In progress, thousands impacted
For 22 years, all 6th graders from public, parochial, and homeschool attend to learn lessons in conservation | Splash event: watershed, common water, trees, pollinators, earthworms, nematodes, and soil health |  | Adams County SWCD | Annually |  | In progress, thousands impacted
Adult education | Various field days focused on water quality and soil health topics | Cooperative Amish Outreach grant, Demo Farm grant, and various other funding sources | Adams & Allen County SWCDs, and other partners | Annually |  | In progress, hundreds impacted
Provide education materials explaining the WLEB and how actions affect others (promotes BMPs), how watersheds are connected and effect one another, and proper management of manure and how it effects phosphorus in the soil | Adams County Watershed, Adams County Watershed Maps, and Manure Management Practices booklets | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2016 |  | Complete, hundreds dispersed
Education on cover crops and how it helps phosphorous levels on farms | Cover Crop PARP meeting | Center Seeds | Center Seeds, Purdue Extension, and Adams County SWCD | 2016 |  | Complete, over a hundred impacted
Public promotion of soil health and water quality (combined annual meeting of SWCD, Farm Bureau, and Pork Producers) | Ag extravaganza |  | Adams County SWCD, Pork Producers, and Farm Bureau | Annually |  | In progress, hundreds impacted
Education of proper management of manure and reducing our phosphorous and education on value of manure and the IN State Chemist standards | Winter ag meeting | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Designed and disbursed nutrient management packets to encourage manure management and to ease record keeping for our producers | Nutrient management packets | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 2017 |  | Complete
Education on importance of soil testing and the levels of phosphorous, soil health and best management practices are encouraged, as well as follow-up meeting to interpret test and provide aerial map of farm | Soil testing | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 6/2015 through 6/2017 |  | Complete, over a hundred tests
Education on the importance of manure and its value and a follow-up farm visit | Manure tests | Amish Outreach grant | Adams County SWCD, NRCS, and ISDA | 6/2015 through 6/2017 |  | Complete
Provide education on WLEB, phosphorous levels in our area, and water and marine life testing | OSU Stone Lab tour on Lake Erie | Demo Farm grant | Adams County SWCD, NRCS, and ISDA | 2017-06-01 |  | Complete
Two meetings (am and pm) regarding education on WLEB, effects on phosphorous, water quality, and benefits and use of gypsum | Connect the Dots water quality meeting | Amish Outreach grant, Dr. Chris Winslow | Adams County SWCD, NRCS, and ISDA | 2016-03-14 |  | Complete
Promote use and benefits of cover crops and no-till practices, specifically drill being modified to be pulled by horses or tractor | Purchase of new Land Pride 7’ no-till drill | Demo Farm grant | Adams County SWCD and NRCS | 2017-06-01 |  | Complete
Educate on a variety of stormwater and water quality related topics to neighborhood groups and other organizations | Speakers available to discuss stormwater and water quality related topics | Staff time, as well as meeting and material expenses | City of Fort Wayne Utilities |  |  | In progress
Hands-on rain garden workshops and incentives for City of Fort Wayne residents to install a rain garden | Hands-on rain garden workshop held locally in Fort Wayne to provide rain garden and stormwater education | Staff time, meeting and material expenses, travel expenses, and incentives to Fort Wayne residents | City of Fort Wayne Utilities | Annual meetings typically held in spring |  | In progress